## Summary
PUBLIC PROCUREMENT REGULATORY AUTHORITY
GENERAL PROCUREMENT NOTICE - SUMMARY
Made pursuant to Regulation 18 (1&2) of GN No 446 of 2013
Name of Procuring Entity |  | Tanzania Geothermal Development Company Limited
No. | Source | Number of Tenders | Total Approved Budget for Planned Procurement (Tshs)
1 | Development | 15 | 6794472082
2 | Recurrent | 39 | 1606598724
3 | Others | 0 | 0
| Total | 54 | 8401070806
Planned Procurement
No. | Category | Number of Tenders | Total Value (Tshs)
1 | Goods | 28 | 989798010
2 | Works | 9 | 2457325380
3 | Consultancy Services | 6 | 4252146702
4 | Non-Consultancy services | 11 | 701800714
5 | Disposal of Public Assets | 0 | 0
| Total | 54 | 8401070806
Planned Methods of Procurement
No. | Category | Number of Tenders | Total Value (Tshs)
1 | International Competitive Bidding (ICB/ICS) | 1 | 150000000
2 | National competitive bidding (NCB/NCS) | 10 | 5314472082
3 | Competitive quotation (CQ) | 13 | 484220000
4 | Single source (SS) | 5 | 1270600000
5 | Individual Selection (IS) | 2 | 45000000
6 | CUIS Framework Agreement | 23 | 1136778724
| Total | 54 | 8401070806
This report is generated from TANePS on 08/12/2021

## Data
Procuring Entity | Tanzania Geothermal Development Company Limited
Procurement Plan for financial year | 2021/2022
Date Last Updated | 2021-07-14 09:46
Comments
[9 empty] | Basic data |  |  | Prequalification/Request for Expression of Interest |  |  | Invitation for Bids and Contract Award
# | Procurement Category | UNSPSC | Is CUIS? | Tender No | Description of the Procurement | Budget Purpose | Source of Funds | Procurement Method | Selection Method | Contract Type | Gen.Proc Notice Advert | Invitation Date | Closing Opening | Applicant Notification Date | Invitation Date | Submission / Opening Date | Approval of evaluation report | Notice of intention to award Date | Vetting / Ratification of contracts | Award Notification Date | Comments
1 | Goods | 14111509 | Yes | PA/131/2021-2022/HQ/G/01 | Supply of Stationery and Office Supplies | Recurrent
2 | Goods | 44100000 | Yes | PA/131/2021-2022/HQ/G/02 | Supply of ICT Equipment and Consumables | Recurrent
3 | Goods | 44100000 | Yes | PA/131/2021-2022/HQ/G/03 | Supply of Video Conference Equipment | Recurrent
4 | Goods | 45121510 | No | PA/131/2021-2022/HQ/G/04 | Supply of Drone Camera | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
5 | Goods | 44100000 | Yes | PA/131/2021-2022/HQ/G/05 | Supply and Installation of Anti-Virus | Recurrent
6 | Goods | 81111702 | No | PA/131/2021-2022/HQ/G/06 | Supply, Installation and Commissioning of Local Area Network at TGDC Dodoma Office and Mbeya Office | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
7 | Goods | 56101700 | Yes | PA/131/2021-2022/HQ/G/07 | Supply of Office Furniture | Recurrent
8 | Goods | 46161600 | Yes | PA/131/2021-2022/HQ/G/08 | Supply of Dispensed Drinking Water | Recurrent
9 | Goods | 53102700 | Yes | PA/131/2021-2022/HQ/G/09 | Supply of Staff Uniforms, Ceremonial Dresses, Sports Wears and Safety Gears | Recurrent
10 | Goods | 40101701 | Yes | PA/131/2021-2022/HQ/G/10 | Supply of HIV Protective Gears | Recurrent
11 | Goods | 40101701 | Yes | PA/131/2021-2022/HQ/G/11 | Supply of Air Conditioners | Recurrent
12 | Goods | 30000000 | Yes | PA/131/2021-2022/HQ/G/12 | Supply of Building Materials | Recurrent
13 | Goods | 53131622 | Yes | PA/131/2021-2022/HQ/G/13 | Supply of Tyres and Batteries | Recurrent
14 | Goods | 15100000 | Yes | PA/131/2021-2022/HQ/G/14 | Supply of Diesel | Recurrent
15 | Goods | 55101515 | No | PA/131/2021-2022/HQ/G/15 | Printing and Supply of Promotional Materials | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-13 | 2021-10-20 | 2021-10-25
16 | Goods | 55101515 | No | PA/131/2021-2022/HQ/G/16 | Printing and Binding of Board Charter and Legal Guidelines | Recurrent | Government | MVP - Minor Value Procurement |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-07-27 | 2021-08-02 | 2021-08-04
17 | Goods | 39121436 | No | PA/131/2021-2022/HQ/G/17 | Supply of Electrodes | Recurrent | Government | SST - Single Source Tendering |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-08-03 | 2021-08-11 | 2021-08-13 | 2021-08-19 | 2021-09-08
18 | Goods | 41112206 | Yes | PA/131/2021-2022/HQ/G/18 | Supply of GPS | Recurrent
19 | Goods | 41114500 | No | PA/131/2021-2022/HQ/G/19 | Supply of Mechanical, Electrical and Electronic Spare Parts | Recurrent | Government | MVP - Minor Value Procurement |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-07-27 | 2021-08-02 | 2021-08-04
20 | Goods | 42172001 | Yes | PA/131/2021-2022/HQ/G/20 | Supply of First Aid Kit | Recurrent
21 | Goods | 27111509 | Yes | PA/131/2021-2022/HQ/G/21 | Supply of Sensor Cable and Transmitter Fuse | Recurrent
22 | Goods | 12161503 | Yes | PA/131/2021-2022/HQ/G/22 | Supply of Chemicals and Field Consumambles | Recurrent
23 | Goods | 12161503 | No | PA/131/2021-2022/HQ/G/23 | Supply of Auger Machine | Recurrent | Government | MVP - Minor Value Procurement |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-07-27 | 2021-08-02 | 2021-08-04
24 | Goods | 25172100 | No | PA/131/2021-2022/HQ/G/24 | Supply, Installation and Commissioning of Car Track System | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
25 | Goods | 55101504 | No | PA/131/2021-2022/HQ/G/25 | Supply of News Papers | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
26 | Goods | 30240000 | No | PA/131/2021-2022/HQ/G/26 | Supply of Consumables for Direct Use Drier | Development | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
27 | Goods | 12161503 | No | PA/131/2021-2022/HQ/G/27 | Consumables for Hachery and Spring Logger | Development | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
28 | Goods | 42251600 | No | PA/131/2021-2022/HQ/G/28 | Supply of Physical Exercise Equipment | Recurrent | Government | MVP - Minor Value Procurement |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-07-27 | 2021-08-02 | 2021-08-04
29 | Non Consulting Services | 78111500 | No | PA/131/2021-2022/HQ/NC/01 | Provision of Air Tickets Services | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
30 | Non Consulting Services | 71123005 | Yes | PA/131/2021-2022/HQ/NC/02 | Provision of Cleaning Services | Recurrent
31 | Non Consulting Services | 92121504 | Yes | PA/131/2021-2022/HQ/NC/03 | Provision of Security Services | Recurrent
32 | Non Consulting Services | 60105405 | No | PA/131/2021-2022/HQ/NC/04 | Provision of Insurance for Motor Vehicles | Recurrent | Government | SST - Single Source Tendering |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-08-03 | 2021-08-11 | 2021-08-12 | 2021-08-24 | 2021-08-26
33 | Non Consulting Services | 44100000 | Yes | PA/131/2021-2022/HQ/NC/05 | Service and Maintenance of Motor Vehicles | Recurrent
34 | Non Consulting Services | 60105405 | No | PA/131/2021-2022/HQ/NC/06 | Provision of Insurance for Geothermal Equipment | Recurrent | Government | SST - Single Source Tendering |  |  | 2021-07-01 |  |  |  | 2021-07-12 | 2021-08-03 | 2021-08-11 | 2021-08-12 | 2021-08-24 | 2021-08-26
35 | Non Consulting Services | 44100000 | Yes | PA/131/2021-2022/HQ/NC/07 | Provision of Routine Maintenance and Repair of Office Equipment | Recurrent
36 | Non Consulting Services | 47100000 | No | PA/131/2021-2022/HQ/NC/08 | Removal of Sewage Water | Recurrent | Government | NS - National Shopping |  |  | 2021-07-01 |  |  |  | 2021-09-13 | 2021-09-20 | 2021-09-30 | 2021-10-04 | 2021-10-13 | 2021-10-20
37 | Non Consulting Services | 43200000 | Yes | PA/131/2021-2022/HQ/NC/09 | Provision of Internet Services | Recurrent
38 | Non Consulting Services | 71123005 | Yes | PA/131/2021-2022/HQ/NC/10 | Provision of Catering Services | Recurrent
39 | Non Consulting Services | 90111600 | Yes | PA/131/2021-2022/HQ/NC/11 | Provision of Conference Facilities | Recurrent
40 | Works | 72130000 | No | PA/131/2021-2022/HQ/W/01 | Construction of Water and Road Infrastructures at Kiejo-Mbaka Geothermal Prospect in Mbeya Region for Women Special Group | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
41 | Works | 1017302800 | No | PA/131/2021-2022/HQ/W/02 | Construction of Water and Road Infrastructures at Songwe Geothermal Prospect in Songwe Region for Women Special Group | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
42 | Works | 71120000 | No | PA/131/2021-2022/HQ/W/03 | Drilling of Two (2) Shallow Wells at Songwe Geothermal Prospect in Songwe Region | Development | Government | SST - Single Source Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-27 | 2021-10-04 | 2021-10-04 | 2021-10-15 | 2021-10-21
43 | Works | 49240000 | No | PA/131/2021-2022/HQ/W/04 | Construction of Geothermal Recreational centre, Acquaculture Facilities and associated Infrastructures for Direct Use Projects at Songwe Geothermal Prospect in Songwe Region | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
44 | Works | 49240000 | No | PA/131/2021-2022/HQ/W/05 | Drilling of Four (4) Test Wells at Kiejo-Mbaka Geothermal Prospect in Mbeya Region | Development | Government | SST - Single Source Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-27 | 2021-10-04 | 2021-10-04 | 2021-10-15 | 2021-10-21
45 | Works | 72130000 | No | PA/131/2021-2022/HQ/W/06 | Construction of Geothermal Recreational centre, Acquaculture Facilities and associated Infrastructures for Direct Use Projects at Kiejo-Mbaka Geothermal Prospect in Mbeya Region | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
46 | Works | 72130000 | No | PA/131/2021-2022/HQ/W/07 | Construction of Geothermal Recreational centre, Acquaculture Facilities and associated Infrastructures for Direct Use Projects at Luhoi Geothermal Prospect in Pwani Region | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
47 | Works | 72130000 | No | PA/131/2021-2022/HQ/W/08 | Construction of Geothermal Recreational centre, Acquaculture Facilities and associated Infrastructures for Direct Use Projects at Ibadakuli Geothermal Prospect in Shinyanga Region | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
48 | Works | 72130000 | No | PA/131/2021-2022/HQ/W/09 | Construction of temporary storage, workshop, rest house, office facilities at Songwe Geothermal Prospect in Songwe Region | Development | Government | NCT - National Competitive Tendering |  |  | 2021-07-01 |  |  |  | 2021-09-06 | 2021-09-20 | 2021-09-27 | 2021-09-27 | 2021-10-07 | 2021-10-15
49 | Consulting Services | 80101508 | No | PA/131/2021-2022/HQ/C/01 | Provision of Consultancy Services for Valuation of Company Assets | Recurrent | Government | CS - Individual Consultant Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-05-10 | 2021-05-31 | 2021-06-10 | 2021-06-14 | 2021-06-21 | 2021-07-05
50 | Consulting Services | 80121600 | No | PA/131/2021-2022/HQ/C/02 | Provision of Consultancy Service for Legal Opinion | Recurrent | Government | CS - Individual Consultant Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-05-10 | 2021-05-31 | 2021-06-10 | 2021-06-14 | 2021-06-21 | 2021-07-05
51 | Consulting Services | 80101601 | No | PA/131/2021-2022/HQ/C/03 | Provision of Consultancy Services for Supervision of Detailed Surface Study at Natron Geothermal Prospect in Arusha region | Development | Government | NCS - National Competitive Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-09-23 | 2021-10-26 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-20 | Geothermal is a new industry in Tanzania, currently we do not have experts in the country.
52 | Consulting Services | 80101601 | No | PA/131/2021-2022/HQ/C/04 | Provision of Consultancy Services for Supervision of Detailed Surface Study at Natron Geothermal Prospect in Arusha region | Development | Government | NCS - National Competitive Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-09-23 | 2021-10-26 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-20 | Geothermal is a new industry in Tanzania, currently we do not have experts in the country.
53 | Consulting Services | 80101601 | No | PA/131/2021-2022/HQ/C/05 | Provision of consultancy Services for Planning, Designing, Supervision and Management of Infrastructure and Drilling Programme of two (2) shallow wells at Songwe Geothermal Prospect in Mbeya Region | Development | Government | ICS - International Competitive Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-09-23 | 2021-10-26 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-20 | Geothermal is a new industry in Tanzania, currently we do not have experts in the country.
54 | Consulting Services | 80101601 | No | PA/131/2021-2022/HQ/C/06 | Provision of Consultancy Service for Pre-feasibility Study of Geothermal Resource at Songwe geothermal Prospect in Mbeya region | Development | Government | NCS - National Competitive Selection | QCBS | Lumpsum | 2021-07-01 | 2021-08-05 | 2021-08-27 | 2021-09-03 | 2021-09-23 | 2021-10-26 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-20 | Geothermal is a new industry in Tanzania, currently we do not have experts in the country.